## Risk Register
Risk register template
Risk # | Date raised | Risk description |  |  | Risk owner | Control information | Control effectiveness |  | Controlled level of risk (risk rating) |  |  | Treatments |  |  |  | Residual level of risk |  |  | Risk status
|  | Risk description If YYY this may result in XXX | Potential causes | Possible consequences |  | Current controls | Control design | Control operaton | Likelihood | Consequence | Controlled level of risk | Planned or required treatments | Due date | Action owner | Status of treatment implementation | Likelihood | Consequence | Residual level of risk | Open/ closed
1 | DD/MM/YY | If we do not address the issue of increased number of student complaints, this may result in a reduction in the number of student registrations/students deciding to leave our institution | Lack of understanding of student needs/course expectation | Lose of revenue, lose of reputation, reduction on the number of available courses | Faculty Head | Individual 1 to 1 sessions with students to help mitigate complaints | Partially effective | Partially effective | Possible | Extreme | High 22 | Review of student complaints to understand the nature of complaints and develop a remediation plan to address concerns and/or manage expectations. | DD/MM/YY | Faculty Head | Review still needs to be undertaken | Unlikely | Major | Medium 14 | Open

## Heat Map
See instructions on how to use the heatmap below in the 'Instructions' tab
LIKELIHOOD |  | Medium | Medium | High | Extreme | Extreme
Event occurs in most or all circumstances.
| Event occurs every 6 months or more often. | 11 | 16 | 20 | 23 | 25
More than a 90% chance event will occur during the next 6 months.
|  | Medium | Medium | High | High | Extreme
Event occurs frequently.
| Event occurs every 6–12 months. | 7 | 12 | 17 | 21 | 24
75–90% chance event will occur during the next 12 months.
|  | Low | Medium | Medium | High | High
Event could occur at some time.
| Event occurs every 1–2 years. | 4 | 8 | 13 | 18 | 22
50–75% chance event will occur during the next 12 months.
|  | Low | Low | Medium | Medium | High
Event occurs in exceptional circumstances.
| Event occurs every 2–4 years. | 2 | 5 | 9 | 14 | 19
10–50% chance event will occur in the next 12 months.
|  | Low | Low | Medium | Medium | Medium
Event is unexpected or unforeseen.
| Event occurs every 4 or more years. | 1 | 3 | 6 | 10 | 15
Less than 10% chance event will occur during the next 12 months.
CONSEQUENCE
|  | Insignificant | Minor | Moderate | Major | Extreme
Financial |  | Disruption to financial/budget activities of less than [$25,000]. | Disruption to financial/budget activities of [$25,000–$100,000]. | Disruption to financial/budget activities of [$100,000–$250,000]. | Disruption to financial/budget activities of [$250,000–$500,000]. | Disruption to financial/budget activities of [$500,000 or more].
|  | <5% impact to total project budget or capital expenditure. | 5–15% impact to total project budget or capital expenditure. | 15–30% impact to total project budget or capital expenditure. | 30–50% impact to total project budget or capital expenditure. | >50% impact to total project budget or capital expenditure.
Project & programme delivery |  | Schedule delay, cost increase or scope change for a specific singular deliverable, no impact on overall project delivery or "cost baseline” (aka budget). | Schedule delay, cost increase or scope change for some deliverables, minimal impact on overall project delivery or “cost baseline” (aka budget). | Schedule delays (up to 3 months) or scope changes. | Schedule delays (up to 6 months) or scope changes/reduction. | Significant schedule, scope, cost, quality or non-financial resource changes that mean the project is no longer viable.
|  | No impact to quality of project deliverable(s), product or service. | Minor impact to quality of project deliverable(s)/ product/service, and to non-financial resourcing. | Cost increases requiring use of some project “Management Reserve” (aka contingency). | Cost increases requiring use of all project “Management Reserve” (aka contingency). | Additional funding beyond the original “Total Project Budget” required, ie, new funding bid would be necessary.
|  | No impact to identified benefits. | All identified benefits possible, but realisation is delayed for a single benefit. | Moderate impact to project deliverable(s)/product/service quality, and to non-financial resourcing. | Major impact to project deliverable(s)/ product/service quality, and to non-financial resourcing. | No benefit realisation.
|  | No impact to non-financial resourcing. | Intentionally Blank | All identified benefits possible, but realisation is delayed for >1 benefit. | Benefit realisation is not possible for 1 benefit, or realisation is delayed for >2 / all benefits. | Intentionally Blank
Service delivery |  | Low quality service, falling short of customer expectations. | Service degradation with periodic stoppages of a key function/service (<3 working days). | Service failure with short term stoppages of key functions/services (1–2 weeks). | Service failure with medium term stoppages of key functions/services (2–4 weeks). | Service failure with a sustained stoppage of key functions/services (>1 month).
|  | Not expected to have an impact on customer satisfaction. | Minor impact on customer satisfaction, with some complaints. | Organisation performance falling well short of customer expectations. | Negative shift in overall customer satisfaction score for current year. | Systemic failure that undermines systems.
|  | Intentionally Blank | Intentionally Blank | Short-term negative impact on customer satisfaction, increasing numbers of complaints. | Intentionally Blank | Systems compromised by external threat (eg, cyber security intrusion).
|  | Intentionally Blank | Intentionally Blank | Intentionally Blank | Intentionally Blank | Customer satisfaction score negatively impacted for more than one year.
Legal/regulatory |  | Insignificant legal or regulatory issues (eg, self-reported non-compliance) with no investigation or censure. | Minor legal or regulatory issues resulting in limited investigation or censure. | Moderate legal or regulatory issues resulting in investigation and censure. | Major legal or regulatory issues resulting in investigation and public censure (eg, Public Service Commission, Ombudsman, Office of the Auditor General etc). | Significant legal or regulatory issues resulting in investigation and very serious public censure (eg, Public Service Commission, Ombudsman, Office of the Auditor General etc).
Privacy and security |  | Very small number of people impacted (eg, 1–5). | Small number of people impacted (eg, 5–10). | Moderate number of individuals impacted (eg, 11–100), with moderate potential/ actual harm. | Large number of individuals impacted (eg, 100 –1,000). | Very large number of individuals impacted (eg, 1,000 or more).
|  | Very low sensitivity of information involved (eg, name, contact details). | Low/minor sensitivity of information involved (eg, name contact details, role/position details. | Moderately sensitive information involved (eg, biographic information, employment details, CVs). | Highly sensitive information involved (eg, biometric information, passport and immigration details, financial, health, criminal records). | Significantly sensitive information involved (eg, biometric, passport/immigration details, financial, health, criminal records, information about at-risk people, vulnerable people contact details).
|  | No potential or little actual harm. | Minor potential/actual harm to individuals. | Potential for harm to individuals. | Serious potential/actual harm to individuals. | Significant potential/actual harm to individuals.
People |  | Minimal capability/capacity gaps. | Minor capability/capacity gaps. | Some capability/capacity gaps. | Major capability/capacity gaps in key business areas. | Significant capability/capacity gaps in key business areas.
|  | Minimal impacts to staff engagement. | Slight decline in staff engagement. | Some staff unable to adapt to change. | Some staff resistance to transformational change. | Much staff resistance to transformational change.
|  | No retraining required. | Minor retraining required. | Noticeable decline in staff engagement. | Major retraining required. | Significant drop in employee engagement.
|  | Injury/illness causing temporary pain and/or discomfort with no first aid required, no lost time and no long-term effects. | An injury requiring first aid, minimal time lost and no long-term effects. | Some retraining required. | Considerable hospitalisation required; significant time lost. | Extensive retraining required.
|  | Intentionally Blank | Intentionally Blank | An injury/occupational illness requiring off-site medical attention, with some lost time. | Intentionally Blank | One or more fatalities or a notifiable incident: significant lost time and/or office shut down.
Reputational |  | No loss in confidence in a specific service or the organisation. | Reduced confidence in a specific service. | Reduced confidence in the organisation. | High profile loss of confidence in the organisation with stakeholders (including the Minister) are publicly critical of organisation’s performance. | Complete loss of confidence in the organisation.
|  | Few or no complaints. | A small number of complaints. | Adverse national media attention. | Major and ongoing negative national media coverage. | Minister publicly expresses loss of confidence in organisation CEO and/or Board.
|  | Little local media interest. | Minor negative local media coverage. | Increasingly negative activity on social media. | Sustained negative activity on social media. | Major stakeholders lobby for change at the organisation.
|  | A few negative posts/comments on social media. | Targeted negative social media activity. | Stakeholders are critical of organisation's performance. | Intentionally Blank | Sustained negative national and international media coverage (including social media).
|  | Existing guidance addresses any issues or concerns. | Poor practice highlighted and raised internally within the organisation. | Poor practices that external parties are aware off. | Intentionally Blank | Intentionally Blank

## Instructions
Instructions
Purpose
1 | The heatmap should be used when determining the scoring associated with 'Likelihood' and 'Consequence' in your risk register.
2 | 'Likelihood' represents the expected occurrence of an event over a period and/or how many times it will happen each time an event occurs. You will need to make your own judgement call when deciding.
3 | 'Consequence' represents what will happen to your organisation if an event does occur.
4 | 'Consequence' is themed up across several disciplines in your organisation. You will need to take your organisation’s specific circumstances into account and adjust the weightings, where appropriate, eg, $500,000 for your organisation may be too high as a measure. You could adjust this down to $50,000 and do the same for other weightings.
Note
5 | An exemplar has been added to the risk register to help you understand how to complete it.
6 | Controlled level of risk represents your existing risk.
7 | Residual risk represents the risk that will remain after remediation measures have been put in place.

## Lists (hidden)
|  | Combination |  |  |  | Control effectiveness | Status
Likelihood | Impact
Rare | Insignificant | Rare | Extreme | RareExtreme | Medium 15 | Effective | Open
Unlikely | Minor | Unlikely | Extreme | UnlikelyExtreme | High 19 | Partially effective | Closed
Possible | Moderate | Possible | Extreme | PossibleExtreme | High 22 | Ineffective
Likely | Major | Likely | Extreme | LikelyExtreme | Extreme 24
Almost Certain | Extreme | Almost Certain | Extreme | Almost CertainExtreme | Extreme 25
|  | Rare | Major | RareMajor | Medium 10
|  | Unlikely | Major | UnlikelyMajor | Medium 14
|  | Possible | Major | PossibleMajor | High 18
|  | Likely | Major | LikelyMajor | High 21
|  | Almost Certain | Major | Almost CertainMajor | Extreme 23
|  | Rare | Moderate | RareModerate | Medium 6
|  | Unlikely | Moderate | UnlikelyModerate | Medium 9
|  | Possible | Moderate | PossibleModerate | Medium 13
|  | Likely | Moderate | LikelyModerate | High 17
|  | Almost Certain | Moderate | Almost CertainModerate | High 20
|  | Rare | Minor | RareMinor | Low 3
|  | Unlikely | Minor | UnlikelyMinor | Low 5
|  | Possible | Minor | PossibleMinor | Medium 8
|  | Likely | Minor | LikelyMinor | Medium 14
|  | Almost Certain | Minor | Almost CertainMinor | Medium 16
|  | Rare | Insignificant | RareInsignificant | Low 1
|  | Unlikely | Insignificant | UnlikelyInsignificant | Low 2
|  | Possible | Insignificant | PossibleInsignificant | Low 4
|  | Likely | Insignificant | LikelyInsignificant | Medium 7
|  | Almost Certain | Insignificant | Almost CertainInsignificant | Medium 11